## Dashboard
Project Status Dashboard
Live insights into project health, timelines, and key milestones
Overall Project Completion | 58%
Task Status Summary
Not Started | 1
In Progress | 1
Completed | 1
On Hold | 1
Blocked | 1
Next Milestone In | 2

## Project Plan
Task ID | Task Name | Start Date | End Date | Duration (Days) | Progress (%) | Milestone | Progress Duration | Milestone Date | Status | Assigned To | Priority
1 | Project Initiation | 2025-04-08 | 2025-04-09 | 2 | 100 | Yes | 2 | 45757 | Not Started | Ali | High
2 | Requirements Gathering | 2025-04-10 | 2025-04-14 | 5 | 100 | No | 5 | #N/A | In Progress | Sana | Medium
3 | Design Phase | 2025-04-15 | 2025-04-21 | 7 | 60 | No | 4.2 | #N/A | Completed | John | Low
4 | Development Phase | 2025-04-22 | 2025-05-09 | 18 | 30 | No | 5.4 | #N/A | On Hold | Fatima | Medium
5 | Testing & Deployment | 2025-05-10 | 2025-05-20 | 11 | 0 | Yes | 0 | 45798 | Blocked | Zara | Critical

## Data
Status | Assigned To | Priority
Not Started | Ali | High
In Progress | Sana | Medium
Completed | John | Low
On Hold | Fatima | Medium
Blocked | Zara | Critical